## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Sprint 2
Team Name | SWEN-261-Team-d-Scrummaster
Simple Move | PASS - a single piece depending on color is able to make a simple move on the checkerboard - ASW | 2018-04-02
Single Jump Move | PASS - a single piece depending on color is able to make a jump move on the checkerboard - ASW | 2018-04-02
King | PASS - piece is able to convert to a king. - ASW | 2018-04-02
Destroy Piece | PASS - a piece occupying a space below another piece's jump was cleared off the checkerboard - ASW | 2018-04-02
End Turn | FAIL - receiving NullPointerExceptions and different outputs from what is expected. - ASW | 2018-04-02
Sprint 1
Team Name | SWEN-261-Team-d-Scrummaster
Web Application Interface | PASS - The web interface functions correctly - AH | 2018-04-07
Start a Game | PASS - A player is able to start a game - AH | 2018-04-07
Player Sign-in | PASS - A player is able to sign in - AH | 2018-04-07
Invite Selected Opponents | PASS - A player is able to select an opponent | 2018-04-07
Two Players | PASS - Two players are able to play at the same time | 2018-04-07
Player Logout | PASS - A player can logout | 2018-04-07
Initilize Board State | PASS - The board is created correctly | 2018-04-07
Connect with selected Opponents | PASS - A player is able to connect with another player | 2018-04-07

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | AH 4/6/18
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | AH 4/6/18
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | AH 4/6/18
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | AH 4/6/18
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | AH 4/6/18
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | AH 4/6/18
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | AH 4/6/18
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. | Pass | AH 4/6/18
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | AH 4/6/18
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | AH 4/6/18
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | AH 4/6/18
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | AH 4/6/18 - Doesn't return to home page just pops up a message
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | AH
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | AH
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | AH
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. | Pass | AH
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | AH
As a player, I want to be able to invite specific opponent so that we can connect to each other online | Given that I am on the home page when I want to play a game of checkers then I expect to see a method to look for my opponent. | Pass | AH 4/6/18
| Given that I am a player on the home page when I want to play a game of checkers then I expect to have the control to invite my opponent to a game. | Pass | AH 4/6/18
| Given that I am a player on the home page when I want to play a game of checkers then I expect to see a list of all avaliable players. | Pass | AH 4/6/18
| Given that I am a player when I select a player, I expect to see if a player is busy. | Pass | AH 4/6/18
| Given that I am a player when I select a player, I expect to sucessfully start a game with them if they are not in a game. | Pass | AH 4/6/18
| Given that I am a player when I am on the home page, I expect to see the total number of other players online. | Pass | AH 4/6/18
As a Player, I must be able to play against a Second Player in a game of checkers so that I abide by the American rules. | Given that I am a player playing a game of checkers, when I connect to a game then I expect that I will be playing against another opponent. | Pass | AH 4/6/18
| Given that I am a player playing a game of checkers, when I connect to a game then I expect to see the name of my opponent | Fail | Doesn't appear on the second client when running two different web browsers
| Given that I am a player playing a game of checkers, when I see my opponent, I expect it to be the same one I chose on the home page | Pass | AH 4/6/18
| Given that I am a player playing a game of checkers, when I join the game, I expect only one other person to connect. | Pass | AH 4/6/18
| A player when connecting to another player in the game of checkers should connect to each other via the internet so they can play a game of Web Checkers |  | Unkown if it works outside of localhost
| Given a valid game startup If I was the one who started the game, I expect to make the first move | Pass | AH 4/6/18
As a Player, I want to log out so that I can close my session and re-login a later time. | Given that I am a player at the home page, when I click logout then I expect to be signed out from the website and, return to the signin page. | Pass | AH 4/7/18
| Given that I am a player I expect to see a button that I can click in order to logout. | Pass | AH 4/7/18
| Given that I am a player when I logout I expect my user name to become avaliable for another player | Pass | AH 4/7/18
| Given that I am a player when I logout I expect to be able to sign back in with another un-taken name | Pass | AH 4/7/18
As a player, I want to be able to start up a game with an initial board state following the standard checkers American rules so I can play a fair game of web checkers. | Given that I am a player who is logged in when I want to start a game with another opponent then I expect the board to be set up for the start of the game. | Pass | AH 4/6/18
| Given that I am a player who is logged in when I want to start a game with another opponent then I expect to see the checker pieces set up for both my opponent and me. | Pass | AH 4/6/18
Given that I am a player who is logged in when I start a game with another opponent then I expect boxes for information and controls
| Given that I am a player who is logged in when I start a game, then I expect the board to be an 8x8 grid | Pass | AH
| Given that I am a player who is logged in when I start a game, then I expect each player to have 12 pieces in the correct locations | Pass | AH
| Given that I am a player I expect to see the controls, Backup, Submit turn, and Resign in the top right of the screen | Fail | AH 4/7/18 The second player's controls don't show up when using two seperate browsers
| Given that I am a player I expect to see the Info bar containing the names of the players | Fail | AH 4/7/18 The second players' info only shows white and red no names when using two sperate browsers.
| Given that I am a player when I view the info bar I expect it to highlight which player's turn it is | Fail | AH 4/7/18 The second player's info bar doesn't highlight anything
| Given that I am a player I expect to see in text whos turn it is. | Fail
Given that I am a player when I click the signout button on the game page, I expect to automatically resign from the current game.
As a player, I want to be able to connect to a specific opponent so that we can begin to play online versus each other | Given that I am player logged in when I select an opponent who is also logged in, to play a game, then I expect to connect with this player | Pass | AH 4/6/18
| Given I am a player logged in when I select an opponent to play a game, then I expect to see a confirmation verifying that I am able to connect with my opponent. | Pass | AH 4/6/18
| Given I am a player logged in, when I select an opponent to play a game, then I expect to be taken to the game board with said opponent | Pass | AH 4/6/18
Players will be able to move one square diagonally forward. | Given that I am a player playing checkers with an opponent when I click and hold a checker piece on the checkerboard then I expect to move my checker piece onto the appropriate square. | Pass | AH 4/6/18
| Given that I am a player playing checkers with an opponent when I click and hold a checker piece on the checkerboard then I expect to move my checker piece not to be able to move onto a enemy players piece |  | Unknown
| Given that I am a player playing checkers with an opponent when I click and hold a checker piece on the checkerboard then I expect my piece not to be able to move to a non diagonal square. | Pass | AH 4/6/18
| Given that I am a player, playing checkers with an opponent when I attempt a move, I expect to only be able to move only one space diagonally. | Pass | AH 4/6/18
| Given that I am a player, when I make my move, I expect the black square I moved from and the square I am moving to, to be highlighted green | Pass | AH 4/6/18
A player will be able to jump over an opponent's piece and capture it. This only handles a single move. | Given that I am a player, and one of my pieces is in a spot to legally capture an enemy piece, I expect to be able to jump over that piece and land diagonally one space past it. |  | Unknown - AH 4/6/18
Given that I am a player, when one of my pieces jumps over an enemy's piece, remove that piece.
Given that I am a player when I execute a jump move, I expect to be able to make another valid move if applicable.
Given that I am a player when I go to make a jump move, and there is an piece on the square diagonally behind the enemy piece, I expect to not be able to jump over said piece.
When a player's piece makes it to the last row at the end of the board, make that player's piece a king | Given that I am a player, when I move my piece to the last row at the end of the board, I expect that piece to become a king
Given that I am a player, when I am controlling a king piece I expect it to be able to execute a single move backwards and forwards
Given that I am a player, when I am controlling a king piece I expect it to be able to execute a jump move backwards and forwards
Given that I am a player, when I have a king piece that is jumped over, I expect it to be removed like a normal piece
Given that I am a player, when I am controlling a king piece, I expect it to still follow the standard rules found in single jump
As a player, I want to be able to destroy an enemy's piece. | Given that I am a player, when I execute a jump move over an enemy piece, I expect that piece to be removed from play.
Given that I am a player, when I destroy a piece, I expect to be able to move a piece into the space the previous piece resided in.
As a Player, I want to end the turn when I am done deciding what I want to do. | Given that I am a player, when I move my pieces, I expect to see a way to submit my turn
Given that I am a player who has finished making their moves, when I submit my moves, I expect the game to update the enemy's board
Given that I am a player who has finished making their moves, when I submit my moves, I expect the game to allow my enemy to make their moves.
As a player I expect to be able to forfit a game | Given that I am a player playing checkers when I click resign then I except to be able to leave that game of checkers.
Given that I am a player, when I want to resign, I expect to see some way to do so
Given that I am a player playing checkers when I click resign then I except to see a notification that I have resigned the game to my opponent.
Given that I am a player playing checkers when I click resign then I except to return back to the homepage.
Given that I am a player who is in a game, when I click the signout button I expect to automaticlly resign from my current game.
As a Player, I want the game to end since I have won or lost the game. | Given that I am a player playing a game when all my pieces are off the board, I expect to have lost the game
Given that I am a player, when I win, I expect to see a message informing me I have won
Given that I am a player, when I lose, I expect to see a message informing me I have lost
Given that I am a player, when only my color pieces remain on the board, I expect to have won
Given that I am a player, when I win or lose, I expect to be returned to the home page
Given that I am a player, when I forfit, I expect to lose